## Slide 1: UKHSA-AIR-RIS- Use Case development Weekly reports

## Slide 2
OFFICIAL
Project Update |UKHSA-AIR-RIS- AI Readiness Use Case Development 06/03
B. KEY ACCOMPLISHMENTS THIS PERIOD | 
General Submitted security architecture statement to support non prod AWS account vend WS2 Investigated Docling versus Textract. Agreed with other data scientists in our meeting to use docling as the default extractor. Tested extraction features from main branch. Successfully configured Docling locally from the main branch. Worked on bug fixes of extraction features that weren’t working. Close collaboration between UCD and engineering to ensure alignment on wireframes. Revised metadata ingestion approach. Finalised MVP design of search results. Finished restructuring the code organisation Implemented the documents services. Implemented batch upload of document. Working on deployment configuration (infra-as-code). Defined basic public API for the front end. Defined interfaces for extractors and embedders. | 
C. Key Activities next period | 
Continue with making Docling work on AWS. Test extraction with Docling from AWS Port over Docling highlighting feature that worked in the POC over to main branch through code refactoring. Write documentation for the features. Finalise MVP design of gap map Begin testing of semantic search in production-like environment | 
D. KEY ISSUES REQUIRING MANAGEMENT ATTENTION / AWARENESS | 
ATTENTION (HELP NEEDED) | AWARENESS (REASONS)
A. EXECUTIVE SUMMARY
The team made strong technical and design progress across the extraction pipeline, application architecture, and user‑facing components. Docling was confirmed as the default extraction tool following comparative analysis, with successful configuration and testing from the main branch. Collaboration between UCD and engineering ensured alignment on wireframes, while the metadata ingestion approach was refined and the MVP design for search results was finalised. Significant backend and infrastructure work was completed, including restructuring the codebase, implementing document services and batch upload, progressing infra‑as‑code deployment configuration, and defining both the public API and interfaces for extractors and embedders
E. KEY MILESTONES (DUE FOR THE CURRENT AND NEXT PERIOD + OVERDUE + AT RISK) |  |  |  |  |  | 
ID | Milestone Name | Plan Date | Forecast | LP | CP | Comment
 | D07 – AI Use case Exemplar | 31 Mar | 31 Mar | G | G | 
 | D08 – AI High level Operating Model | 31 Amr | 31 Mar | G | G | 
F. KEY RISKS |  |  |  | 
ID | TOP 3 RISKS TO BE ADDRESSED | MITIGATION | CS | Conf
UKHSA-AIR-RIS-19 | Risk: The solution may not progress to Private Beta. Cause: The project may not receive access to the UKHSA Production AWS account in time. Impact: UKHSA teams would need to complete the remaining deployment pipeline after the Informed Solutions team rolls off at the end of March. | Submit a TRB request promptly to secure production‑level approval from key UKHSA stakeholders. 26/2 Steering group agreed that the Private Beta user access will be on a non production environment | G | M
UKHSA-AIR-RIS-03 | There is a risk: Additional budget may be required, requested and approved. As a result of: incurred cloud hosting and computing costs for deployment of the Private Beta solution Will lead to: delays whilst the approval process is running. | Estimate required cloud resources once the Proof of Concept environment is defined. Confirm expected usage with FinOps, understand the current cloud budget approval process, and secure funding early. | A | H
UKHSA-AIR-RIS-18 | There is a risk: Use of any AI related technology breaches UKHSA licence agreement with the CLA on copyright As a result of: UHKSA being bound by NHS licence agreement. Will lead to: Prohibition of use of AI technology for non generative non training applications | We have isolated a solution that we believe is compliant with the licence agreement, and this will be played back to the business in the steering group for acceptance. UKHSA to provide a legal interpretation of the licence terms to confirm compliance of the selected use case. | G | 
LP – Last Period CP – Current Period LS – Score for LP CS – Score for CP Conf – Confidence Level
 | Time |  |  |  | Cost |  | Personnel |  |  | Dependencies | Benefits | Overall

## Slide 3: Previous reports

## Slide 4
OFFICIAL
Project Update |UKHSA-AIR-RIS- AI Readiness Use Case Development 20/02
B. KEY ACCOMPLISHMENTS THIS PERIOD | 
General Excellent engagement twith the UKHSA SecArch and progress on the cyber governance is proceeding. Support from this forum has laid the SC vetting risk to bed Project is now stood up in UKHSA JIRA WS2 implemented complete body of evidence collection pipeline (ingestion -> extraction -> embedding) started work on Document management service implemented parsing of RIS documents for metadata started work on infrastructure configurations and deployment coordination with the team on API for the frontend rapid development of wireframes, and close collaboration with the software engineers as they developed functional prototypes of the search tools WS3 Continuing Meeting with stakeholders providing updates on the WS3 work Iterating the work following feedback from the stakeholder meetings | 
C. Key Activities next period | 
Continue working with SecArch to complete cyber security to review architecture and roadmap Ongoing story creation Continue work on the Document management service Continue working on infra config and deployment Developing out the prototypes Show and Tell | 
D. KEY ISSUES REQUIRING MANAGEMENT ATTENTION / AWARENESS | 
ATTENTION (HELP NEEDED) | AWARENESS (REASONS)
A. EXECUTIVE SUMMARY
TStrong engagement with UKHSA SecArch has advanced cyber‑governance activity, resolved the SC‑vetting risk, and the project is now fully established in UKHSA JIRA. WS2 delivered major technical progress, completing the evidence‑collection pipeline, advancing the document‑management service, implementing metadata parsing, progressing infrastructure setup, and producing early prototypes in close collaboration with engineering. WS3 continued stakeholder engagement, iterating outputs in line with feedback.
E. KEY MILESTONES (DUE FOR THE CURRENT AND NEXT PERIOD + OVERDUE + AT RISK) |  |  |  |  |  | 
ID | Milestone Name | Plan Date | Forecast | LP | CP | Comment
 | D07 – AI Use case Exemplar | 31 Mar | 31 Mar | G | G | 
 | D08 – AI High level Operating Model | 31 Amr | 31 Mar | G | G | 
F. KEY RISKS |  |  |  |  | 
ID | TOP 3 RISKS TO BE ADDRESSED | MITIGATION |  | CS | Conf
UKHSA-AIR-RIS-19 | Risk: The solution may not progress to Private Beta. Cause: The project may not receive access to the UKHSA Production AWS account in time. Impact: UKHSA teams would need to complete the remaining deployment pipeline after the Informed Solutions team rolls off at the end of March. | Submit a TRB request promptly to secure production‑level approval from key UKHSA stakeholders. 26/2 Steering group agreed that the Private Beta user access will be on a non production environment |  | G | M
UKHSA-AIR-RIS-03 | There is a risk: Additional budget may be required, requested and approved. As a result of: incurred cloud hosting and computing costs for deployment of the Private Beta solution Will lead to: delays whilst the approval process is running. | Estimate required cloud resources once the Proof of Concept environment is defined. Confirm expected usage with FinOps, understand the current cloud budget approval process, and secure funding early. |  | A | H
UKHSA-AIR-RIS-18 | There is a risk: Use of any AI related technology breaches UKHSA licence agreement with the CLA on copyright As a result of: UHKSA being bound by NHS licence agreement. Will lead to: Prohibition of use of AI technology for non generative non training applications | We have isolated a solution that we believe is compliant with the licence agreement, and this will be played back to the business in the steering group for acceptance. UKHSA to provide a legal interpretation of the licence terms to confirm compliance of the selected use case. |  | G | 
LP – Last Period CP – Current Period LS – Score for LP CS – Score for CP Conf – Confidence Level
 | Time |  |  |  | Cost |  | Personnel |  |  | Dependencies | Benefits | Overall

## Slide 5
OFFICIAL
Project Update |UKHSA-AIR-RIS- AI Readiness Use Case Development 20/02
B. KEY ACCOMPLISHMENTS THIS PERIOD | 
General Attended the Cyber Front door MDT call and have had several calls with Cyber and now have a SPOC withing the team to support the project. WS2 - Ingestion and extraction feature complete and working in coordination - Alternative extractors enabled (docling and Kreuzberg, working on Textract) Body of evidence pipeline functional from ingestion to chunking Infrastructure & AWS Architecture Delivered a fully serverless, event‑driven AWS architecture with secure vector search, automated ingestion, and a production‑ready deployment plan. Data Ingestion & AI Pipeline Built a robust AI‑driven ingestion pipeline using Textract and Bedrock to extract layouts, metadata, embeddings, and process historical PDFs at scale. Backend App & Database (FastAPI) Developed a FastAPI backend with seamless PDF upload, search processing, OpenSearch pagination fixes, and a SQLite database for user/workspace tracking. Frontend UI & Search Features Implemented a GOV.UK‑style interface supporting hybrid, multimodal, and S3/FAISS search modes with built‑in benchmarking tools. Debugging, Refactoring & Optimisation Resolved ingestion, API, and database issues while refining search logic and improving data integrity across the application. Documentation & Costing - Produced detailed cost estimates and comprehensive onboarding documentation for setup, deployment, and ongoing operations. WS3 - Meeting with stakeholders to provide an overview of the work that has been done to date on the AI Governance model | 
C. Key Activities next period | 
Engaging with cyber security to review architecture and roadmap Continue user story creation and defining acceptance criteria Continue iterating user journeys and UX designs Continue working on Embedding component Finalising metadata requiremhts for documents | 
D. KEY ISSUES REQUIRING MANAGEMENT ATTENTION / AWARENESS | 
ATTENTION (HELP NEEDED) | AWARENESS (REASONS)
A. EXECUTIVE SUMMARY
The programme made strong progress this period, advancing core technical delivery. Engagement with Cyber has improved and we’ve been assigned a dedicated SPOC to support the work. Key technical components are now in place: ingestion and extraction capabilities are complete and operating, supported by multiple extractor options. The end‑to‑end evidence pipeline is fully functional, and the team has deployed a production‑ready, serverless AWS architecture that enables secure vector search and automated ingestion. Significant enhancements were also delivered across the application stack. The ingestion pipeline now processes historical PDFs at scale using Textract ; the FastAPI backend and database provide stable support for uploads, search, and workspace tracking; and the GOV.UK‑style frontend enables search with benchmarking capability. In parallel, WS3 progressed with stakeholder engagement on the AI Governance model, ensuring alignment as the programme moves toward upcoming phases.
E. KEY MILESTONES (DUE FOR THE CURRENT AND NEXT PERIOD + OVERDUE + AT RISK) |  |  |  |  |  | 
ID | Milestone Name | Plan Date | Forecast | LP | CP | Comment
 | D07 – AI Use case Exemplar | 31 Mar | 31 Mar | G | G | 
 | D08 – AI High level Operating Model | 31 Amr | 31 Mar | G | G | 
F. KEY RISKS |  |  |  | 
ID | TOP 3 RISKS TO BE ADDRESSED | MITIGATION | CS | Conf
UKHSA-AIR-RIS-19 | Risk: The solution may not progress to Private Beta. Cause: The project may not receive access to the UKHSA Production AWS account in time. Impact: UKHSA teams would need to complete the remaining deployment pipeline after the Informed Solutions team rolls off at the end of March. | Submit a TRB request promptly to secure production‑level approval from key UKHSA stakeholders. | R | M
UKHSA-AIR-RIS-05 | There is a risk: that the UKHSA cyber security forum insist on the Informed Team to be SC vetted As a result of: the team having access to Confluence and JIRA. Will lead to: loss of momentum, or a pause in the development work. | Informed solutions have key individuals within the team that are SC cleared and cab provide oversight on the teams activities. The team ask the SRO to accept the risk that they are not all SC cleared | R | M
UKHSA-AIR-RIS-03 | There is a risk: Additional budget may be required, requested and approved. As a result of: incurred cloud hosting and computing costs for deployment of the Private Beta solution Will lead to: delays whilst the approval process is running. | Estimate required cloud resources once the Proof of Concept environment is defined. Confirm expected usage with FinOps, understand the current cloud budget approval process, and secure funding early. | A | H
UKHSA-AIR-RIS-18 | There is a risk: Use of any AI related technology breaches UKHSA licence agreement with the CLA on copyright As a result of: UHKSA being bound by NHS licence agreement. Will lead to: Prohibition of use of AI technology for non generative non training applications | We have isolated a solution that we believe is compliant with the licence agreement, and this will be played back to the business in the steering group for acceptance. UKHSA to provide a legal interpretation of the licence terms to confirm compliance of the selected use case. | G | 
LP – Last Period CP – Current Period LS – Score for LP CS – Score for CP Conf – Confidence Level
 | Time |  |  |  | Cost |  | Personnel |  |  | Dependencies | Benefits | Overall

## Slide 6
OFFICIAL
Project Update |UKHSA-AIR-RIS- AI Readiness Use Case Development 12/02
B. KEY ACCOMPLISHMENTS THIS PERIOD | 
General Attended the TAC‑B governance forum to present the proposed approach for non‑production environments. WS2 Submitted the request for a non‑production AWS account, progressing the prerequisites for environment setup. Continued to advance the emerging solution and technical architecture, aligning with the UCD team’s ongoing work—particularly across data ingestion, extraction, embedding, and search. Completed a first draft of the end‑to‑end technical architecture, providing a clearer baseline for validation and next‑stage design discussions. Worked jointly with the UCD team to define the MVP scope for private beta, ensuring close alignment between user needs, feasibility, and delivery priorities. Held a technical deep‑dive with the Guidance Search Team’s data scientists (Toby Nonnenmacher, Laurence, Felix Feldman) focusing on model selection, validation approaches, and knowledge sharing on text embedding. Met with Clair Dobie and Nev Reid to review AI‑related AWS cost considerations, including approaches to monitoring, forecasting, and managing cloud expenditure for the AI use case. Brian presented at the AI OpenShift webinar last week, contributing insight into our architecture and approach (not captured in the previous report). 4x User research sessions held with evidence reviewers in CCHS, socialising designs and getting feedback User stories created Walked Accenture through our use case to ensure no duplication / cross-over Ingestion component code complete Code quality and security tooling selected and implemented Extraction component in progress, initial tests WS3 Working on the ai product lifecycle. Mapping specific risks of AI to the GDS digital product lifecycle | 
C. KEY ACTIVITIES PLANNED NEXT SPRINT | 
working on screening questions to identify low risk projects that can avoid the full controls in order to allow for quick innovation Continue user story creation and defining acceptance criteria Backlog prioritisation with CCHS Continue working on Embedding component | 
D. KEY ISSUES REQUIRING MANAGEMENT ATTENTION / AWARENESS | 
ATTENTION (HELP NEEDED) | AWARENESS (REASONS)
The project will present at TRB on Monday 16th We'll be asking for authorisation on an AWS vend request for Dev/Test/Preprod environments. We would appreciate some help in ensuring that the request is expedited once its approved. | 
A. EXECUTIVE SUMMARY
The team made strong progress this period, presenting the non‑production environment approach at TAC‑B and advancing core technical delivery. The first end‑to‑end architecture is now drafted, AWS environment setup is underway, and key components—including ingestion and security tooling—are complete. Collaboration with UCD defined the MVP for private beta, supported by user research sessions and new user stories. Stakeholder alignment continues to strengthen through technical deep‑dives, AWS cost reviews, and engagement with Accenture. Work also progressed on the AI product lifecycle and mapping AI‑specific risks to the GDS framework.
E. KEY MILESTONES (DUE FOR THE CURRENT AND NEXT PERIOD + OVERDUE + AT RISK) |  |  |  |  |  | 
ID | Milestone Name | Plan Date | Forecast | LP | CP | Comment
 | D07 – AI Use case Exemplar | 31 Mar | 31 Mar | G | G | 
 | D08 – AI High level Operating Model | 31 Amr | 31 Mar | G | G | 
F. KEY RISKS |  |  |  | 
ID | TOP 3 RISKS TO BE ADDRESSED | MITIGATION | CS | Conf
UKHSA-AIR-RIS-19 | Risk: The solution may not progress to Private Beta. Cause: The project may not receive access to the UKHSA Production AWS account in time. Impact: UKHSA teams would need to complete the remaining deployment pipeline after the Informed Solutions team rolls off at the end of March. | Submit a TRB request promptly to secure production‑level approval from key UKHSA stakeholders. | R | M
UKHSA-AIR-RIS-05 | There is a risk: that the private beta use case may stall As a result of: budget availability and lack of commercial vehicle to complete the work. Will lead to: loss of momentum, missed benefits and additional work to deliver later. | Begin joint planning for post-March activities as early as possible, including business case, resource requirements, timelines, and ownership. Establish a clear roadmap for private beta, public beta, and operationalisation. | A | M
UKHSA-AIR-RIS-03 | There is a risk: Additional budget may be required, requested and approved. As a result of: incurred cloud hosting and computing costs for deployment of the Private Beta solution Will lead to: delays whilst the approval process is running. | Estimate required cloud resources once the Proof of Concept environment is defined. Confirm expected usage with FinOps, understand the current cloud budget approval process, and secure funding early. | A | H
UKHSA-AIR-RIS-18 | There is a risk: Use of any AI related technology breaches UKHSA licence agreement with the CLA on copyright As a result of: UHKSA being bound by NHS licence agreement. Will lead to: Prohibition of use of AI technology for non generative non training applications | We have isolated a solution that we believe is compliant with the licence agreement, and this will be played back to the business in the steering group for acceptance. UKHSA to provide a legal interpretation of the licence terms to confirm compliance of the selected use case. | G | 
LP – Last Period CP – Current Period LS – Score for LP CS – Score for CP Conf – Confidence Level
 | Time |  |  |  | Cost |  | Personnel |  |  | Dependencies | Benefits | Overall

## Slide 7
OFFICIAL
Project Update |UKHSA-AIR-RIS- AI Readiness Use Case Development 06/02
B. KEY ACCOMPLISHMENTS THIS PERIOD | 
General Issued D05 and D06 as per the agreed schedule On boarded additional resources WS2 Defined the general architecture, with a detailed plan for the ingestion and extraction stages. Made decisions with regards to core technology to be used. Ongoing research into implementation options for external services and deployment platform. Established the code structure. Early implementation in place, ongoing development. We have a first draft of our high-level journey map User feedback informed higher-fidelity mock-ups of both the search and search results pages Completion of logical architecture diagrams (System Context and Container/Application Diagrams) Detailed low-level design diagrams identifying specific cloud technologies also drafted WS3 begin defining objectives, roles and responsibilities and risk matrix. | 
C. KEY ACTIVITIES PLANNED NEXT SPRINT | 
Issue D05 / D06 Ongoing UR interviews and analysis Continue Iterate HL user journey map in line with UR findings Iterate LLD and use case diagrams Define chunking strategy Build ANTS code locally | 
D. KEY ISSUES REQUIRING MANAGEMENT ATTENTION / AWARENESS | 
ATTENTION (HELP NEEDED) | AWARENESS (REASONS)
Decision - Vector Embedding will be persisted within a database. - DS&G Data Science Hub - Confluen… Decision - AWS Deployment for Evidence Gap Mapping use-case - DS&G Data Science Hub - Confluence | 
A. EXECUTIVE SUMMARY
The programme has delivered strong momentum this period, issuing D05 and D06 to schedule and onboarding further resources to support delivery. Significant technical progress has been achieved, including defining the overall architecture, establishing detailed ingestion and extraction plans, agreeing core technology decisions, and advancing early implementation with a structured code foundation. Service design has moved forward with a first draft of the high‑level user journey map, user‑informed mock‑ups, and completion of both logical and low‑level architecture diagrams. WS3 has also begun shaping objectives, roles, responsibilities, and the project’s risk matrix, strengthening readiness for the next phase.
E. KEY MILESTONES (DUE FOR THE CURRENT AND NEXT PERIOD + OVERDUE + AT RISK) |  |  |  |  |  | 
ID | Milestone Name | Plan Date | Forecast | LP | CP | Comment
 | D05 – Roadmap and business case development | O6 Feb | 06 - Feb | G | G | 
 | D05 – draft | 02 Feb | 02-Feb | G | G | 
 |  |  |  |  | G | 
 | D06 – Readiness Assessment – Final review and handover | 06 Feb | 06 Feb | G | G | 
 | D06 – Draft | 02 Feb | 02 Feb | G | G | 
 | D07 – AI Use case Exemplar | 31 Mar | 31 Mar | G | G | 
 | D08 – AI High level Operating Model | 31 Amr | 31 Mar | G | G | 
F. KEY RISKS |  |  |  |  | 
ID | TOP 3 RISKS TO BE ADDRESSED | MITIGATION | LS | CS | Conf
UKHSA-AIR-RIS-05 | There is a risk: that the private beta use case may stall As a result of: budget availability and lack of commercial vehicle to complete the work. Will lead to: loss of momentum, missed benefits and additional work to deliver later. | Begin joint planning for post-March activities as early as possible, including business case, resource requirements, timelines, and ownership. Establish a clear roadmap for private beta, public beta, and operationalisation. | N/A | A | M
UKHSA-AIR-RIS-03 | There is a risk: Additional budget may be required, requested and approved. As a result of: incurred cloud hosting and computing costs for deployment of the Private Beta solution Will lead to: delays whilst the approval process is running. | Estimate required cloud resources once the Proof of Concept environment is defined. Confirm expected usage with FinOps, understand the current cloud budget approval process, and secure funding early. | N/A | A | H
UKHSA-AIR-RIS-18 | There is a risk: Use of any AI related technology breaches UKHSA licence agreement with the CLA on copyright As a result of: UHKSA being bound by NHS licence agreement. Will lead to: Prohibition of use of AI technology for non generative non training applications | We have isolated a solution that we believe is compliant with the licence agreement, and this will be played back to the business in the steering group for acceptance. UKHSA to provide a legal interpretation of the licence terms to confirm compliance of the selected use case. | N/A | G | 
LP – Last Period CP – Current Period LS – Score for LP CS – Score for CP Conf – Confidence Level
 | Time |  |  | Cost |  | Personnel |  |  | Dependencies | Benefits | Overall

## Slide 8
OFFICIAL
Project Update |UKHSA-AIR-RIS- AI Readiness Use Case Development 2/2
B. KEY ACCOMPLISHMENTS THIS PERIOD | 
Ways of working adopted Sprint planning for S1 Service design and UR - personas / user needs / users are progressing UR interviews underway Reviewed alpha UR outputs in preparation for Alpha phase Business confirmation on direction of use case development Drafting D05 /D06 ahead of submission 6th Feb Engagement with DXC to discuss options for supporting the delivery Note: 3 planned meetings with Accenture had to be cancelled due to Accenture’s delivery commitments. Roadmap for 26/27 AI investment and delivery issues to Raj/Nick for comment. | 
C. KEY ACTIVITIES PLANNED NEXT SPRINT | 
Issue D05 / D06 Ongoing UR interviews and analysis Iterate HL user journey map in line with UR findings Request for raw UR outputs from CCHS alpha HLD and use case diagrams Define chunking strategy Define content extraction strategy Decide development language and framework Build ANTS code locally | 
D. KEY ISSUES REQUIRING MANAGEMENT ATTENTION / AWARENESS | 
ATTENTION (HELP NEEDED) | AWARENESS (REASONS)
RO access to the AWS account where the bedrock models for ANTS are running for Tom R VDI desktops issued include no developer tools. Support would be appreciated in expediting access to the relevant developer and data science toolchain. | -We may need our developers to be issued a UKHSA laptop to access ANTS – this is being investigated
A. EXECUTIVE SUMMARY
A success in the project delivery has been securing agreement on the use case problem statement and conceptual solution, in response to the copyright issue that surfaced at the beginning of the week, presenting significant risk to the previously proposed Evidence Gap Mapping Use Case. With the use case now fully agreed the team is on track to commence Alpha phase on Monday 02 February. User research is underway, to crystalise the user needs and Alpha hypotheses. UR activities will continue with business users and stakeholders through the coming Alpha phase. The ways of working have been agreed by the team, including Zalaya and a full member of the multidisciplinary team. Informed will l be rescheduling our internal calls and bringing the CCHS business users closer into the team to provide support and maintain engagement and clarity through delivery. DXC has expressed an interest in pursuing the Global News Bot Use case as a separate sub-squad in parallel with the above use case. DXC are currently proposing their approach and assembling a delivery team.
E. KEY MILESTONES (DUE FOR THE CURRENT AND NEXT PERIOD + OVERDUE + AT RISK) |  |  |  |  |  | 
ID | Milestone Name | Plan Date | Forecast | LP | CP | Comment
 | D05 – Roadmap and business case development | O6 Feb | 06 - Feb | G | G | 
 | D05 – draft | 02 Feb | 02-Feb | G | G | 
 |  |  |  |  | G | 
 | D06 – Readiness Assessment – Final review and handover | 06 Feb | 06 Feb | G | G | 
 | D06 – Draft | 02 Feb | 02 Feb | G | G | 
 | D07 – AI Use case Exemplar | 31 Mar | 31 Mar | G | G | 
 | D08 – AI High level Operating Model | 31 Amr | 31 Mar | G | G | 
F. KEY RISKS |  |  |  |  | 
ID | TOP 3 RISKS TO BE ADDRESSED | MITIGATION | LS | CS | Conf
UKHSA-AIR-RIS-05 | There is a risk: that the private beta use case may stall As a result of: budget availability and lack of commercial vehicle to complete the work. Will lead to: loss of momentum, missed benefits and additional work to deliver later. | Begin joint planning for post-March activities as early as possible, including business case, resource requirements, timelines, and ownership. Establish a clear roadmap for private beta, public beta, and operationalisation. | N/A | A | M
UKHSA-AIR-RIS-03 | There is a risk: Additional budget may be required, requested and approved. As a result of: incurred cloud hosting and computing costs for deployment of the Private Beta solution Will lead to: delays whilst the approval process is running. | Estimate required cloud resources once the Proof of Concept environment is defined. Confirm expected usage with FinOps, understand the current cloud budget approval process, and secure funding early. | N/A | A | H
UKHSA-AIR-RIS-18 | There is a risk: Use of any AI related technology breaches UKHSA licence agreement with the CLA on copyright As a result of: UHKSA being bound by NHS licence agreement. Will lead to: Prohibition of use of AI technology for non generative non training applications | We have isolated a solution that we believe is compliant with the licence agreement, and this will be played back to the business in the steering group for acceptance. UKHSA to provide a legal interpretation of the licence terms to confirm compliance of the selected use case. | N/A | G | 
LP – Last Period CP – Current Period LS – Score for LP CS – Score for CP Conf – Confidence Level
 | Time |  |  | Cost |  | Personnel |  |  | Dependencies | Benefits | Overall

## Slide 9
OFFICIAL
Project Update |UKHSA-AIR-RIS- AI Readiness Use Case Development 26/1
B. KEY ACCOMPLISHMENTS THIS PERIOD | 
Initial TRB session – Project presented for an FYI session and received no questions or further actions for TRB. Suggested next steps were architectural presentation at TACB and keep both forums updated Sessions held with Zalaya and other key business stakeholders WS2 is in Sprint 0 (discovery) WS03 has commenced and key stakeholder engagement planned for next week Initial conversations with Accenture and DXC around resourcing a blended team have been progressing. | 
C. KEY ACTIVITIES PLANNED NEXT PERIOD | 
Continued service design and UR - personas / user needs / users Create HL user journey map Book UR slots Review alpha UR outputs – request for raw UR outputs HLD and use case diagrams Integrate business users into the core team and define WoW | 
D. KEY ISSUES REQUIRING MANAGEMENT ATTENTION / AWARENESS | 
ATTENTION (HELP NEEDED) | AWARENESS (REASONS)
We need to determine that the approach we are following is permitted within the copyright clause of the current NHS licence | -We may need our developers to be issued a UKHSA laptop to access ANTS -
A. EXECUTIVE SUMMARY
The delivery is on track. The analysis of the selected use case has identified complexity in the bus processes that are presenting challenges in defining a clear problem definition and product scope, Informed is currently pursuing a tool to support human reviewers in evidence evaluation workflow whilst avoiding challenges associated with the NHS licence agreement which bars the use of LLM’s against the source content. There is a hard dependency on confirming the interpretation of the licence agreement such that semantic. database analysis of raw evidence content is a distinct process form the training an prompting of LLM’s
E. KEY MILESTONES (DUE FOR THE CURRENT AND NEXT PERIOD + OVERDUE + AT RISK) |  |  |  |  |  | 
ID | Milestone Name | Plan Date | Forecast | LP | CP | Comment
 | D05 – Roadmap and business case development | O6 Feb | 06 - Feb | N/A | G | 
 | D05 – draft | 02 Feb | 02-Feb | N/A | G | 
 |  |  |  |  | G | 
 | D06 – Readiness Assessment – Final review and handover | 06 Feb | 06 Feb | N/A | G | 
 | D06 – Draft | 02 Feb | 02 Feb | N/A | G | 
 | D07 – AI Use case Exemplar | 31 Mar | 31 Mar | N/A | G | 
 | D08 – AI High level Operating Model | 31 Amr | 31 Mar | N/A | G | 
F. KEY RISKS |  |  |  |  | 
ID | TOP 3 RISKS TO BE ADDRESSED | MITIGATION | LS | CS | Conf
UKHSA-AIR-RIS-05 | There is a risk: that the private beta use case may stall As a result of: budget availability and lack of commercial vehicle to complete the work. Will lead to: loss of momentum, missed benefits and additional work to deliver later. | Begin joint planning for post-March activities as early as possible, including business case, resource requirements, timelines, and ownership. Establish a clear roadmap for private beta, public beta, and operationalisation. | N/A | A | M
UKHSA-AIR-RIS-03 | There is a risk: Additional budget may be required, requested and approved. As a result of: incurred cloud hosting and computing costs for deployment of the Private Beta solution Will lead to: delays whilst the approval process is running. | Estimate required cloud resources once the Proof of Concept environment is defined. Confirm expected usage with FinOps, understand the current cloud budget approval process, and secure funding early. | N/A | A | H
 |  |  | N/A | G | 
LP – Last Period CP – Current Period LS – Score for LP CS – Score for CP Conf – Confidence Level
 | Time |  |  | Cost |  | Personnel |  | Dependencies | Benefits | Overall